## Detailed Analysis
Sino | Module | Functionality | Sub Tasks | Complexity | Design | Develop | Unit Testing | Days Needed
1 | Candidate.ID | Seed User | Administrator Login | Medium | 1 | 2 | 1 | 4
2 | (Admin) | Seed User | Forget Password /Reset | Medium | 1 | 2 | 1 | 4
3 |  | Seed User | Layout Branding | Complex | 2 | 4 | 1 | 7
4 |  |  | Access Clients | Complex | 2 | 4 | 1 | 7
5 |  |  | Manage Clients | Complex | 2 | 4 | 1 | 7
6 |  |  | Client Permissions | Complex | 2 | 4 | 1 | 7
7 |  |  | Client Transperancy | Complex | 2 | 4 | 1 | 7
8 |  |  | Security Settings | Complex | 2 | 4 | 1 | 7
9 |  |  | Reports | Complex | 2 | 4 | 1 | 7
Clients (Tenant)
10 | Settings | Settings/Themes | Theme Download | Medium | 1 | 2 | 1 | 4
11 |  |  | Theme Preview | Complex | 2 | 4 | 1 | 7
12 |  |  | Theme Listing | Medium | 1 | 2 | 1 | 4
12 |  |  | Theme Upload /Install | Complex | 2 | 4 | 1 | 7
13 |  |  | Apply Theme | Complex | 2 | 4 | 1 | 7
Settings /Categories
14 |  |  | Category Boot | Complex | 2 | 4 | 1 | 7
15 |  |  | New Category | Complex | 2 | 4 | 1 | 7
16 |  |  | Category Dynamic Grid | Medium | 1 | 2 | 1 | 4
17 |  |  | Category Grid Edit | Medium | 1 | 2 | 1 | 4
18 |  |  | Category Grid Delete | Medium | 1 | 2 | 1 | 4
19 |  |  | Category Filter | Medium | 1 | 2 | 1 | 4
20 |  |  | Category Search | Medium | 1 | 2 | 1 | 4
21 |  | Settings /Configuration | System Settings / Base | Complex | 2 | 4 | 1 | 7
22 |  |  | System Settings / General | Complex | 2 | 4 | 1 | 7
23 |  |  | System Settings / Defaults | Complex | 2 | 4 | 1 | 7
24 |  |  | System Settings / CORS | Complex | 2 | 4 | 1 | 7
25 |  |  | System Settings / Micsellaneous | Complex | 2 | 4 | 1 | 7
26 |  |  | API Settings / Base | Medium | 1 | 2 | 1 | 4
27 |  |  | API Settings / Task | Complex | 2 | 4 | 1 | 7
[6 empty] | 1 | 1 | 2
28 |  |  | Campaign Settings / Base | Medium | 1 | 2 | 1 | 4
29 |  |  | Campaign Settings | Complex | 2 | 4 | 1 | 7
30 |  |  | Email Settings / Base | Complex | 2 | 4 | 1 | 7
31 |  |  | Email Settings / Mail Sending | Complex | 2 | 4 | 1 | 7
32 |  |  | Email Settings / Default Frequency Rule | Medium | 1 | 2 | 1 | 4
33 |  |  | Email Settings /Monitored Inbox Settings | Complex | 2 | 4 | 1 | 7
34 |  |  | Email Settings /Contact Replies | Complex | 2 | 4 | 1 | 7
35 |  |  | Email Settings / Message Settings | Complex | 2 | 4 | 1 | 7
36 |  |  | Email Settings / Unsubscribe Settings | Complex | 2 | 4 | 1 | 7
37 |  |  | Landing Page Settings / Base | Medium | 1 | 2 | 1 | 4
38 |  |  | Landing Page Settings / Task | Complex | 2 | 4 | 1 | 7
39 |  |  | Tracking Settings / Base | Complex | 2 | 4 | 1 | 7
40 |  |  | Tracking Settings / Visitors Tracking | Complex | 2 | 4 | 1 | 7
41 |  |  | Tracking Settings /FB Pixels | Complex | 2 | 4 | 1 | 7
42 |  |  | Tracking Settings / Google Analytics | Complex | 2 | 4 | 1 | 7
43 |  |  | WebHook Settings / Base | Medium | 1 | 2 | 1 | 4
44 |  |  | WebHook Settings / Task | Complex | 2 | 4 | 1 | 7
45 |  |  | Social Settings / Base | Medium | 1 | 2 | 1 | 4
46 |  |  | Social Settings / Task | Medium | 1 | 2 | 1 | 4
47 |  | Users | Base Screen | Complex | 2 | 4 | 1 | 7
48 |  |  | New Users | Complex | 2 | 4 | 1 | 7
49 |  |  | Filter Users | Complex | 2 | 4 | 1 | 7
50 |  |  | User Edit | Medium | 1 | 2 | 1 | 4
51 |  |  | User Delete | Medium | 1 | 2 | 1 | 4
52 |  |  | Screen Pagination | Medium | 1 | 2 | 1 | 4
53 |  | Roles | Roles Basic Screen | Complex | 2 | 4 | 1 | 7
54 |  |  | New Role / Details | Complex | 2 | 4 | 1 | 7
55 |  |  | New Role / Permissions | Complex | 2 | 4 | 1 | 7
56 |  |  | Role Grid Pagination | Medium | 1 | 2 | 1 | 4
57 |  |  | Roles Edit / Delete | Complex | 2 | 4 | 1 | 7
58 |  |  | Role Filtering | Medium | 1 | 2 | 1 | 4
59 |  | Web Hooks | Base Screen | Medium | 1 | 2 | 1 | 4
60 |  |  | New Web Hook | Complex | 2 | 4 | 1 | 7
61 |  |  | Pagination | Medium | 1 | 2 | 1 | 4
62 |  |  | WebHooks Edit | Medium | 1 | 2 | 1 | 4
63 |  |  | WebHooks Delete | Medium | 1 | 2 | 1 | 4
64 |  |  | Filtering | Medium | 1 | 2 | 1 | 4
65 |  | Custom Fields | Base Screen | Complex | 2 | 4 | 1 | 7
66 |  |  | New Custom Fields | Complex | 2 | 4 | 1 | 7
67 |  |  | Custom Fields Edit | Medium | 1 | 2 | 1 | 4
68 |  |  | Custom Fields Clone | Medium | 1 | 2 | 1 | 4
69 |  |  | Custom Fields Filter | Medium | 1 | 2 | 1 | 4
70 |  | Plugins | Base Screen | Complex | 2 | 4 | 1 | 7
71 |  |  | Plugin Search | Medium | 1 | 2 | 1 | 4
72 |  |  | All Plugins (32 Pluigns) | Complex | 2 | 4 | 1 | 7
Clients ( Tenant)
73 | Core Functions | Dashboard | DashBoard Base Screen | Complex | 2 | 4 | 1 | 7
74 |  |  | Contacts Graph Widget | Complex | 2 | 4 | 1 | 7
75 |  |  | Contact Map Widget | Complex | 2 | 4 | 1 | 7
76 |  |  | Contact Top Lists Widget | Complex | 2 | 4 | 1 | 7
77 |  |  | Contacts Visits Graph Widget | Complex | 2 | 4 | 1 | 7
78 |  |  | Contacts Emails Graph Widget | Complex | 2 | 4 | 1 | 7
79 |  |  | Unique / Returning Visitors View Widget | Complex | 2 | 4 | 1 | 7
80 |  |  | Opened Mails View Widget | Complex | 2 | 4 | 1 | 7
81 |  |  | Anonymus Leads Widget | Complex | 2 | 4 | 1 | 7
82 |  |  | Dwell Times Widget | Complex | 2 | 4 | 1 | 7
83 |  |  | Recet Activity Widget | Complex | 2 | 4 | 1 | 7
84 |  |  | Upcoming Emails Widget | Complex | 2 | 4 | 1 | 7
85 |  |  | Dashboard Export | Complex | 2 | 4 | 1 | 7
86 |  |  | Dashboard Import | Complex | 2 | 4 | 1 | 7
87 |  |  | Dashboard New Widgets | V Complex | 4 | 8 | 1 | 13
88 |  | Calendar | Calendar Base Screen | Complex | 2 | 4 | 1 | 7
89 |  |  | Calendar Navigation Pane Data Binding | Complex | 2 | 4 | 1 | 7
90 |  | Contacts | Contacts Base Screen with Grid | Complex | 2 | 4 | 1 | 7
91 |  |  | Quick Add | Medium | 1 | 2 | 1 | 4
92 |  |  | Quick Add-> Create Company | Complex | 2 | 4 | 1 | 7
93 |  |  | Grid Paging | Medium | 1 | 2 | 1 | 4
94 |  |  | New Contact / Basic | Complex | 2 | 4 | 1 | 7
95 |  |  | New Contact / Social | Complex | 2 | 4 | 1 | 7
96 |  |  | Contacts Export | Complex | 2 | 4 | 1 | 7
97 |  |  | Contacts Import | Complex | 2 | 4 | 1 | 7
98 |  |  | Contacts Import History | Medium | 1 | 2 | 1 | 4
99 |  |  | Contacts Filtering | Medium | 1 | 2 | 1 | 4
100 |  |  | Contacts Enabling Live | Complex | 2 | 4 | 1 | 7
101 |  |  | Contacts Anonymus Toggle | Complex | 2 | 4 | 1 | 7
102 |  |  | Contacts Edit | Medium | 1 | 2 | 1 | 4
103 |  |  | Contacts Delete | Medium | 1 | 2 | 1 | 4
104 |  |  | Conats Send Email | Medium | 1 | 2 | 1 | 4
105 |  |  | Custom Email Editor | Complex | 2 | 4 | 1 | 7
106 |  | Companies | Base Screen Grid | Complex | 2 | 4 | 1 | 7
107 |  |  | New Company / Core | Medium | 1 | 2 | 1 | 4
108 |  |  | New Company /Professional | Medium | 1 | 2 | 1 | 4
109 |  |  | Contacts Count and Display in Grid | Medium | 1 | 2 | 1 | 4
110 |  |  | Company Filter | Medium | 1 | 2 | 1 | 4
111 |  |  | Import Company | Complex | 2 | 4 | 1 | 7
112 |  |  | Import History | Medium | 1 | 2 | 1 | 4
113 |  |  | Grid Pagination | Medium | 1 | 2 | 1 | 4
114 |  |  | Edit Company | Medium | 1 | 2 | 1 | 4
115 |  |  | Clone Company | Medium | 1 | 2 | 1 | 4
116 |  |  | Delete Company | Medium | 1 | 2 | 1 | 4
117 |  | Segments | Segments Screen Grid | Complex | 2 | 4 | 1 | 7
118 |  |  | New Segment / Details | Medium | 1 | 2 | 1 | 4
119 |  |  | New Segment / Filter | Medium | 1 | 2 | 1 | 4
120 |  |  | Segment Filtering / Search | Complex | 2 | 4 | 1 | 7
121 |  |  | Contacts Count and Display in Grid | Complex | 2 | 4 | 1 | 7
122 |  |  | Segment Edit | Medium | 1 | 2 | 1 | 4
123 |  |  | Segment Delete | Medium | 1 | 2 | 1 | 4
124 |  |  | Segment Grid Pagination | Medium | 1 | 2 | 1 | 4
125 |  | Components | Assets / Base Screen | Medium | 1 | 2 | 1 | 4
126 |  |  | Assets / New Asset / Local | Complex | 2 | 4 | 1 | 7
127 |  |  | Assets / New Asset /Remote | Complex | 2 | 4 | 1 | 7
128 |  |  | Assets / New Asset /Remote File Browse | Medium | 1 | 2 | 1 | 4
129 |  |  | Assets / Show Asset Preview | Medium | 1 | 2 | 1 | 4
130 |  |  | Assets / Show Asset Download Graph | Complex | 2 | 4 | 1 | 7
131 |  |  | Assets / Show Asset Details Form | Medium | 1 | 2 | 1 | 4
132 |  |  | Assets /Grid Edit | Medium | 1 | 2 | 1 | 4
133 |  |  | Assets /Grid Delete | Medium | 1 | 2 | 1 | 4
134 |  |  | Assets /Grid Clone | Medium | 1 | 2 | 1 | 4
135 |  |  | Assets /Grid Preview | Medium | 1 | 2 | 1 | 4
136 |  |  | Assets / Grid Sorting /Paging | Medium | 1 | 2 | 1 | 4
137 |  |  | Assets /Filters and Search | Complex | 2 | 4 | 1 | 7
138 |  |  | Forms / Base Screen /Grid | Complex | 2 | 4 | 1 | 7
139 |  |  | Forms /New Campaign Form / Details | Medium | 1 | 2 | 1 | 4
140 |  |  | Forms /New Campaign Form / Fileds | Complex | 2 | 4 | 1 | 7
141 |  |  | Forms /New Campaign Form / Actions | Complex | 2 | 4 | 1 | 7
142 |  |  | Froms / Campain Display | Complex | 2 | 4 | 1 | 7
143 |  |  | Froms / Campain Visit Grid | Complex | 2 | 4 | 1 | 7
144 |  |  | Forms / Campaign Landing Pages | Complex | 2 | 4 | 1 | 7
145 |  |  | Forms / Campaign Edit | Complex | 2 | 4 | 1 | 7
146 |  |  | Forms / Campaign Delete | Medium | 1 | 2 | 1 | 4
147 |  |  | Forms / Campaign Clone | Medium | 1 | 2 | 1 | 4
148 |  |  | Forms / Campaign Preview | Medium | 1 | 2 | 1 | 4
149 |  |  | Forms / Campaign Results | Complex | 2 | 4 | 1 | 7
150 |  |  | Forms / Filtering / Sorting | Complex | 2 | 4 | 1 | 7
151 |  |  | Landing Pages / Base Screen / Themes Grid | Complex | 2 | 4 | 1 | 7
152 |  |  | Landing Pages /View Theme | Medium | 1 | 2 | 1 | 4
153 |  |  | Landing Pages / Display Grid | Medium | 1 | 2 | 1 | 4
154 |  |  | Landing Pages / View Landing Page | Complex | 2 | 4 | 1 | 7
155 |  |  | Landing Pages / Page Visit Graph Widget | Complex | 2 | 4 | 1 | 7
156 |  |  | Landing Pages / New Landing Page | Complex | 2 | 4 | 1 | 7
157 |  |  | Landing Pages / Searching | Medium | 1 | 2 | 1 | 4
158 |  |  | Landing Pages / Edit | Medium | 1 | 2 | 1 | 4
159 |  |  | Landing Pages / Clone | Medium | 1 | 2 | 1 | 4
160 |  |  | Landing Pages / Delete | Medium | 1 | 2 | 1 | 4
161 |  |  | Landing Pages / Grid Paging | Medium | 1 | 2 | 1 | 4
162 |  |  | Landing Pages / View Page DashBoard | Complex | 2 | 4 | 1 | 7
163 |  |  | Dynamic Content / Base Screen Grid | Medium | 1 | 2 | 1 | 4
164 |  |  | Dynamic Content / New Dynamic Cont | Complex | 2 | 4 | 1 | 7
165 |  |  | Dynamic Content / View Dashboard | Complex | 2 | 4 | 1 | 7
166 |  |  | Dynamic Content / View Dash / Visit Graph | Complex | 2 | 4 | 1 | 7
167 |  |  | Dynamic Content / Filter / Sorting | Medium | 1 | 2 | 1 | 4
168 |  |  | Dynamic Content / Grid Pagination | Medium | 1 | 2 | 1 | 4
169 |  |  | Dynamic Content / Edit | Medium | 1 | 2 | 1 | 4
170 |  |  | Dynamic Content / Delete | Medium | 1 | 2 | 1 | 4
171 |  |  | Dynamic Content / Clone | Medium | 1 | 2 | 1 | 4
172 |  | Campaigns | Base Screen / Grid with Paging | Complex | 2 | 4 | 1 | 7
173 |  |  | New Campaign | Medium | 1 | 2 | 1 | 4
174 |  |  | Campaign Builder | Complex | 2 | 4 | 1 | 7
175 |  |  | Campaign / View Dash / Visit Graph | Complex | 2 | 4 | 1 | 7
176 |  |  | Campaign / Filter / Sorting | Medium | 1 | 2 | 1 | 4
177 |  |  | Campaign/ Grid Pagination | Medium | 1 | 2 | 1 | 4
178 |  |  | Campaign / Edit | Medium | 1 | 2 | 1 | 4
179 |  |  | Campaign/ Delete | Medium | 1 | 2 | 1 | 4
180 |  |  | Campaign/ Clone | Medium | 1 | 2 | 1 | 4
181 |  | Channels | Marketing Messages / Base Screen | Complex | 2 | 4 | 1 | 7
182 |  |  | Marketing Messages / New Marketing Message | Complex | 2 | 4 | 1 | 7
183 |  |  | Marketing Messages /Messge Dashboard | Complex | 2 | 4 | 1 | 7
184 |  |  | Marketing Messages /Visit Graph Widget | Complex | 2 | 4 | 1 | 7
185 |  |  | Marketing Messages / Filter / Sorting | Medium | 1 | 2 | 1 | 4
186 |  |  | Marketing Messages / Grid Pagination | Medium | 1 | 2 | 1 | 4
187 |  |  | Marketing Messages / Edit | Medium | 1 | 2 | 1 | 4
188 |  |  | Marketing Messages / Delete | Medium | 1 | 2 | 1 | 4
189 |  |  | Marketing Messages / Clone | Medium | 1 | 2 | 1 | 4
190 |  |  | Email / Basce Screen | Medium | 1 | 2 | 1 | 4
191 |  |  | Email / New Email | Medium | 1 | 2 | 1 | 4
192 |  |  | Email / New Templated Email | Complex | 2 | 4 | 1 | 7
193 |  |  | Email / New Segment Email | Complex | 2 | 4 | 1 | 7
194 |  |  | Email / Email View Dashboard | Complex | 2 | 4 | 1 | 7
195 |  |  | Email /Visit Graph Widget | Complex | 2 | 4 | 1 | 7
196 |  |  | Email / Filter / Sorting | Medium | 1 | 2 | 1 | 4
197 |  |  | Email / Grid Pagination | Medium | 1 | 2 | 1 | 4
198 |  |  | Email / Edit | Medium | 1 | 2 | 1 | 4
199 |  |  | Email / Delete | Medium | 1 | 2 | 1 | 4
200 |  |  | Email/ Clone | Medium | 1 | 2 | 1 | 4
201 |  |  | Focus Items / Base Screen | Medium | 1 | 2 | 1 | 4
202 |  |  | Focus Items / New Focus Items | Complex | 2 | 4 | 1 | 7
203 |  |  | Focus Items/ Focus Items View Dashboard | Complex | 2 | 4 | 1 | 7
204 |  |  | Focus Items /Visit Graph Widget | Complex | 2 | 4 | 1 | 7
205 |  |  | Focus Items/ Filter / Sorting | Medium | 1 | 2 | 1 | 4
206 |  |  | Focus Items / Grid Pagination | Medium | 1 | 2 | 1 | 4
207 |  |  | Focus Items / Edit | Medium | 1 | 2 | 1 | 4
208 |  |  | Focus Items/ Delete | Medium | 1 | 2 | 1 | 4
209 |  |  | Focus Items/ Clone | Medium | 1 | 2 | 1 | 4
210 |  |  | Social Monitoring / Base Screen | Medium | 1 | 2 | 1 | 4
211 |  |  | Social Monitoring / New Social Moniter Entry | Medium | 1 | 2 | 1 | 4
212 |  |  | Social Monitoring / View Dashboard | Complex | 2 | 4 | 1 | 7
213 |  |  | Social Monitoring /Tweet Graph Widget | Complex | 2 | 4 | 1 | 7
214 |  |  | Social Monitoring / Filter / Sorting | Medium | 1 | 2 | 1 | 4
215 |  |  | Social Monitoring / Grid Pagination | Medium | 1 | 2 | 1 | 4
216 |  |  | Social Monitoring / Edit | Medium | 1 | 2 | 1 | 4
217 |  |  | Social Monitoring / Delete | Medium | 1 | 2 | 1 | 4
218 |  | Points | Manage Actions / Base Screen | Medium | 1 | 2 | 1 | 4
219 |  |  | Manage Actions/ New Action | Medium | 1 | 2 | 1 | 4
220 |  |  | Manage Actions/ Filter | Medium | 1 | 2 | 1 | 4
221 |  |  | Manage Actions/ Search | Complex | 2 | 4 | 1 | 7
222 |  |  | Manage Actions/Edit | Medium | 1 | 2 | 1 | 4
223 |  |  | Manage Actions /Delete | Medium | 1 | 2 | 1 | 4
224 |  |  | Manage Actions /Clone | Medium | 1 | 2 | 1 | 4
225 |  |  | Manage Actions /Grid Pagintation | Medium | 1 | 2 | 1 | 4
226 |  |  | Manage Triggers/ Base Screen | Medium | 1 | 2 | 1 | 4
227 |  |  | Manage Triggers/ New Action | Medium | 1 | 2 | 1 | 4
228 |  |  | Manage Triggers/ Filter | Medium | 1 | 2 | 1 | 4
229 |  |  | Manage Triggers/ Search | Complex | 2 | 4 | 1 | 7
230 |  |  | Manage Triggers/Edit | Medium | 1 | 2 | 1 | 4
231 |  |  | Manage Triggers /Delete | Medium | 1 | 2 | 1 | 4
232 |  |  | Manage Triggers /Clone | Medium | 1 | 2 | 1 | 4
233 |  |  | Manage Triggers /Grid Pagintation | Medium | 1 | 2 | 1 | 4
234 |  | Stages | Stages/ Base Screen | Medium | 1 | 2 | 1 | 4
235 |  |  | Stages/ New Action | Medium | 1 | 2 | 1 | 4
236 |  |  | Stages/ Filter | Medium | 1 | 2 | 1 | 4
237 |  |  | Stages/ Search | Medium | 1 | 2 | 1 | 4
238 |  |  | Stages/Edit | Medium | 1 | 2 | 1 | 4
239 |  |  | Stages /Delete | Medium | 1 | 2 | 1 | 4
240 |  |  | Stages/Clone | Medium | 1 | 2 | 1 | 4
241 |  |  | Stages/Grid Pagintation | Medium | 1 | 2 | 1 | 4
242 |  | Reports | Reports / Base Screen | Medium | 1 | 2 | 1 | 4
243 |  |  | Reports/ Filter | Medium | 1 | 2 | 1 | 4
244 |  |  | Reports/ Search | Medium | 1 | 2 | 1 | 4
245 |  |  | Reports/Edit | Medium | 1 | 2 | 1 | 4
246 |  |  | Reports/Delete | Medium | 1 | 2 | 1 | 4
247 |  |  | Reports/Clone | Medium | 1 | 2 | 1 | 4
248 |  |  | Reports/Grid Pagintation | Medium | 1 | 2 | 1 | 4
249 |  |  | Reports /New Report - Assets | Medium | 1 | 2 | 1 | 4
250 |  |  | Reports /New Report -Asset Downloads | Medium | 1 | 2 | 1 | 4
251 |  |  | Reports /New Report -Campaign Events | Medium | 1 | 2 | 1 | 4
252 |  |  | Reports /New Report -Message Queue | Medium | 1 | 2 | 1 | 4
253 |  |  | Reports /New Report -Emails | Medium | 1 | 2 | 1 | 4
254 |  |  | Reports /New Report -Email Sent | Medium | 1 | 2 | 1 | 4
255 |  |  | Reports /New Report -Forms | Medium | 1 | 2 | 1 | 4
256 |  |  | Reports /New Report -Form Subscriptions | Medium | 1 | 2 | 1 | 4
257 |  |  | Reports /New Report -Contacts | Medium | 1 | 2 | 1 | 4
258 |  |  | Reports /New Report -Companies | Medium | 1 | 2 | 1 | 4
259 |  |  | Reports /New Report -Mobile Notifications | Medium | 1 | 2 | 1 | 4
260 |  |  | Reports /New Report -Mobile Notifications Sent | Medium | 1 | 2 | 1 | 4
261 |  |  | Reports /New Report - Landing Pages | Medium | 1 | 2 | 1 | 4
262 |  |  | Reports /New Report -Page Hits | Medium | 1 | 2 | 1 | 4
263 |  |  | Reports /New Report - Data | Simple | 1 | 1 | 1 | 3
264 |  |  | Reports /New Report - Schedule | Simple | 1 | 1 | 1 | 3
265 | General |  | Layout Design and Intergration |  |  |  |  | 10
|  |  | Azure /AWS Settings |  |  |  |  | 10
|  |  | Logging |  |  |  |  | 5
|  |  | Code Quality Analysys |  |  |  |  | 10
|  |  | Others and Buffer |  |  |  |  | 20
[7 empty] | Total | 1460